## DatabaseDesign
Sr. No.	Database Name					VehicleConfigurator
1	Table Name					Segment
	Column name	seg_id	seg_name
	DataType	number	string
	Constraints	primary key
	Validation if any

2	Table Name					Manufacturer
	Column name	man_id	man_name
	DataType	number	string
	Constraints	primary key
	Validation if any

3	Table Name					Variant
	Column name	var_id	seg_id	man_id	var_name	min_qty	base_price	image
	DataType	number	number	number	string	double	double	string
	Constraints	primary key	foreign key	foreign key
	Validation if any					>=20

4	Table Name					Configuration
	Column name	conf_id	var_id	type	configurable	description
	DataType	number	number	string	string	string
	Constraints	primary key	foreign key
	Validation if any				yes/no

5	Table Name					AlternateConf
	Column name	alt_id	conf_id	alt_description	alt_price
	DataType	number	number	string	double
	Constraints	primary key	foreign key
	Validation if any

6	Table Name					Customer
	Column name	company_id	company_name	login_id	password	customer_name	designation	email_id	address_line_1	address_line_2	city	state	pincode	company_tel	customer_mob	vat_no	pan_no	holding
	DataType	number	string	string	string	string	string	string	string	string	number	string	string	string	string	string
	Constraints	primary key		unique				unique					unique	unique
	Validation if any				8-15 characters			abc@def.gh					10 digit	10 digit

## project-schedule
	[Vehicle Configurator]			14-Feb-2021
	[Freelance Training]
	[Shubham Kubal]		02 February 2021

WBS	Task Names	Resource Names	Start	Finish	% Complete

1	Requirement Gathering	shubham	15-Jan-2021	22-Jan-2021	100%

2	Database Design	shubham	23-Jan-2021	28-Jan-2021	100%

3	Backend Development	shubham	29-Jan-2021	31-Jan-2021	100%

4	Frontend Development	shubham	01-Feb-2021	14-Feb-2021	20%

	Vehicle Configuration V1.0.0
	Author: Shubham Kubal <skubal2015@gmail.com>